NexusAI Platform Intelligent Hybrid LLM Orchestration + Universal Automation Architecture Blueprint • MVP Roadmap • Success Index February 2026 ¦ Confidential Draft v1.0

# 1. Executive Summary

NexusAI is a free, open-source, local-first platform that intelligently routes AI tasks between cloud LLMs (Claude, GPT-4, Gemini) and local LLMs (Llama, Mistral via Ollama) based on task complexity, token cost, and data sensitivity. On top of this routing layer, NexusAI provides a unified coding agent and cross-platform automation engine covering Windows, macOS, Linux, and Android/iOS.

Core Value Proposition No single free tool today combines intelligent LLM routing + coding agent + desktop automation + mobile control in one platform. NexusAI fills this gap.

# 2. Market Opportunity & Problem Statement

## 2.1 The Problem

Developers and teams using AI today face three compounding problems:

- Cloud LLM costs spiral out of control on token-heavy tasks like document processing, bulk analysis, and large codebase scanning

- Data privacy risks from sending sensitive code or financial data to cloud APIs

- Fragmented tooling — separate tools for LLM routing, coding agents, and automation with no unified control plane

## 2.2 Target Market Segments

- Solo developers and indie hackers: want local-first AI without ongoing cloud bills

- Regulated industries (fintech, healthcare, legal): must keep sensitive data on-premise; cloud escalation only for non-sensitive reasoning

- DevOps and platform engineering teams: want AI-assisted pipeline automation without vendor lock-in

- Enterprise cost optimization: route 70–80% of token load to local models; reserve paid APIs for high-quality outputs only

## 2.3 Competitive Landscape

| Tool | LLM Routing | Coding Agent | Desktop Auto | Mobile | Free/OSS | Unified Platform |
| --- | --- | --- | --- | --- | --- | --- |
| LiteLLM | ✅ | ❌ | ❌ | ❌ | ✅ | ❌ |
| OpenClaw | ⚠️ | ❌ | ⚠️ | ⚠️ | ✅ | ❌ |
| Cursor | ❌ | ✅ | ❌ | ❌ | ❌ | ❌ |
| n8n | ❌ | ❌ | ❌ | ❌ | ✅ | ❌ |
| AnythingLLM | ⚠️ | ❌ | ❌ | ❌ | ✅ | ❌ |
| YOUR TOOL | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ |

# 3. System Architecture

## 3.1 High-Level Architecture Overview

NexusAI is composed of five interconnected layers. Each layer is independently deployable but works together as a unified control plane.

LAYER 1: Input & Channel Layer CLI • Web UI • REST API • Messaging (Slack, Discord, WhatsApp) • IDE Plugin ↓ LAYER 2: Intelligent Router (Core) Task Classifier • Token Estimator • PII Detector • Cost Budget Enforcer • Failover Logic ↙ ↘ Local LLM Engine (Ollama) Cloud LLM Gateway (Claude/GPT/Gemini) ↘ ↙ LAYER 3: Agent Execution Layer Coding Agent • Task Planner • Memory / Context Store • Tool Executor ↓ LAYER 4: Automation Runtime Windows / macOS / Linux • Android (ADB) • iOS (Shortcuts API) • Browser (Playwright) ↓ LAYER 5: Observability & Control Cost Dashboard • Audit Logs • Usage Analytics • Health Monitor

## 3.2 Intelligent Router — Core Logic

The router is the heart of NexusAI. Its decision logic processes every incoming task through a four-step pipeline:

- Step 1 — Task Classification: A lightweight local classifier (quantized 1B model) labels the task as: planning, bulk-processing, code-generation, or data-extraction

- Step 2 — Token Estimation: Pre-request token count estimate. If estimated tokens exceed configured threshold (default 8,000), route to local LLM

- Step 3 — PII & Sensitivity Scan: Regex + NER model scans for PII patterns. Any hit forces local-only execution regardless of task type

- Step 4 — Budget Enforcement: Per-session and per-day cloud spend caps. When cap is reached, auto-fallback to local model

## 3.3 Coding Agent Integration

The coding agent is built on top of the router, meaning all LLM calls from the agent flow through the intelligent routing layer. Architecture:

- Heavy context tasks (reading entire codebase, scanning 50+ files) → automatically routed to local Llama/Mistral

- Architecture planning, code review, PR summaries → escalated to Claude Opus or GPT-4 via cloud

- Test generation (repetitive, token-heavy) → local model

- Security review and compliance checks → cloud model with audit logging enabled

The agent supports: file read/write, terminal execution, git operations, test runner integration, and diff-based PR creation.

## 3.4 Automation Runtime

NexusAI's automation layer provides cross-platform computer control through a unified Action API. The AI agent emits structured Action objects; the runtime translates them to platform-native calls.

| Layer | Technology | Purpose |
| --- | --- | --- |
| Windows | Win32 API + PyAutoGUI | App control, file ops, system commands, UI interaction |
| macOS | AppleScript + pyobjc + Quartz | Menu bar control, Accessibility API, app scripting |
| Linux | xdotool + wmctrl + bash | X11 window control, terminal automation, file system |
| Browser | Playwright (all OS) | Cross-browser web automation, scraping, form filling |
| Android | ADB (Android Debug Bridge) | App launch, tap/swipe, screenshot, file transfer via USB/WiFi |
| iOS | Apple Shortcuts + SSH bridge | Shortcut triggers, limited automation via Shortcuts API |

# 4. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Router Core | Python + LiteLLM (self-hosted) | Unified LLM proxy, routing rules, budget management, fallbacks |
| Local LLM | Ollama + Llama 3.3 / Mistral / Qwen | Local inference engine, model management, hardware acceleration |
| Task Classifier | Quantized TinyLlama / ONNX model | Fast, local-only routing decision (<50ms latency overhead) |
| Coding Agent | OpenHands (OpenDevin) or Aider | Open-source coding agent, built on top of routing layer |
| Automation | PyAutoGUI + Playwright + ADB | Cross-platform action execution |
| Workflow Builder | React Flow + Node.js backend | Visual pipeline editor for no-code automation |
| UI / Control Plane | Electron or React Web App | Dashboard, model config, cost tracking, logs |
| Memory Store | ChromaDB (local vector DB) | Agent context, conversation history, skill memory |
| Observability | SQLite + OpenTelemetry | Cost tracking, usage analytics, audit trail |
| Packaging | Docker + Docker Compose | Single-command local deployment, works on any OS |

# 5. MVP Roadmap & Phased Delivery

| Phase | Timeline | Deliverables | Success Criteria |
| --- | --- | --- | --- |
| Phase 1 MVP Core | Weeks 1–8 | Intelligent LLM router with Ollama + cloud API support Token & budget enforcement CLI interface Basic web dashboard | Router correctly classifies & routes 90%+ of test tasks <100ms routing overhead Local + cloud model switching works |
| Phase 2 Coding Agent | Weeks 9–16 | Coding agent integration (file read/write, terminal, git) Agent uses router for all LLM calls Context-aware routing (codebase size → local) IDE plugin (VS Code) | Agent completes coding tasks end-to-end 30%+ cost reduction vs pure cloud on benchmarks VS Code plugin installed & working |
| Phase 3 Desktop Auto | Weeks 17–24 | Desktop automation runtime (Win/Mac/Linux) Browser automation via Playwright Visual workflow builder (React Flow) Natural language → automation commands | Automation scripts run successfully on all 3 OSes 10+ pre-built automation templates User can build workflow without writing code |
| Phase 4 Mobile + Scale | Weeks 25–36 | Android automation via ADB iOS via Shortcuts bridge Multi-agent orchestration Plugin/skill marketplace (ClawHub-style) Enterprise features: SSO, audit logs, team management | Android automation working for 80%+ common tasks 20+ community plugins in marketplace Enterprise pilot customers onboarded |

## 5.1 Feature Release Matrix

| Feature | MVP (v1) | v2 | v3 |
| --- | --- | --- | --- |
| Smart LLM Routing (cloud + local) | ✅ | ✅ | ✅ |
| Token-based auto-routing | ✅ | ✅ | ✅ |
| PII detection → force local | ✅ | ✅ | ✅ |
| Cloud cost dashboard | ✅ | ✅ | ✅ |
| Coding agent (file/git/terminal) | ❌ | ✅ | ✅ |
| VS Code / IDE plugin | ❌ | ✅ | ✅ |
| Windows desktop automation | ❌ | ✅ | ✅ |
| macOS desktop automation | ❌ | ✅ | ✅ |
| Linux desktop automation | ❌ | ✅ | ✅ |
| Browser automation (Playwright) | ❌ | ✅ | ✅ |
| Visual workflow builder | ❌ | ⚠️ Partial | ✅ |
| Android automation (ADB) | ❌ | ❌ | ✅ |
| iOS automation (Shortcuts) | ❌ | ❌ | ✅ |
| Multi-agent orchestration | ❌ | ❌ | ✅ |
| Plugin marketplace | ❌ | ❌ | ✅ |
| Team / enterprise features | ❌ | ❌ | ✅ |

# 6. Success Index — NexusAI Winning Score

The NexusAI Success Index measures platform health across six dimensions, each weighted by strategic importance. Total score is calculated out of 100. Target: 75+ for MVP, 85+ for market leadership.

## 6.1 Dimension 1: Technical Execution (Weight: 25%)

Measures whether the core technology actually works reliably and performantly.

| Dimension | Weight | Target Score | Measurement Method |
| --- | --- | --- | --- |
| Routing accuracy (correct model selection) | 8% | ≥ 90% | Automated test suite: 500 diverse tasks, measure correct routing decisions |
| Routing latency overhead | 5% | < 100ms | Benchmark: time delta between direct API call vs routed call |
| Local LLM uptime & stability | 5% | ≥ 99% | 72-hour soak test, measure crash rate and recovery time |
| Automation reliability (cross-platform) | 7% | ≥ 85% | Run 100 automation scripts across Win/Mac/Linux, measure success rate |

## 6.2 Dimension 2: Cost Effectiveness (Weight: 20%)

Measures actual cloud cost savings delivered to users — the primary value proposition.

| Dimension | Weight | Target Score | Measurement Method |
| --- | --- | --- | --- |
| Cloud token cost reduction vs baseline | 10% | ≥ 40% savings | Compare 30-day cloud spend: baseline (no router) vs NexusAI-routed |
| Local model output quality parity | 5% | ≥ 80% quality parity | Human eval: rate local vs cloud output on same tasks, measure gap |
| Budget enforcement accuracy | 5% | 100% enforcement | Set spend cap, verify zero overruns in 100 test sessions |

## 6.3 Dimension 3: Developer Experience (Weight: 20%)

Measures how easy and enjoyable it is to set up, configure, and use the platform.

| Dimension | Weight | Target Score | Measurement Method |
| --- | --- | --- | --- |
| Time-to-first-route (new user setup) | 7% | < 15 minutes | Measure: install → first successful routed LLM call, timed with new users |
| CLI usability score | 5% | ≥ 4.0/5.0 | User survey: 20 beta testers rate CLI UX after first use |
| Documentation completeness | 4% | ≥ 90% coverage | Audit: every feature has doc page, quickstart, and example |
| GitHub stars growth rate (community signal) | 4% | 500+ stars in 90 days | Track GitHub star velocity after launch |

## 6.4 Dimension 4: Market Traction (Weight: 15%)

Measures real-world adoption and evidence that the market wants this product.

| Dimension | Weight | Target Score | Measurement Method |
| --- | --- | --- | --- |
| Active installs (30-day active users) | 6% | 500+ by end of v1 | Telemetry: count unique installs with at least 1 route in past 30 days |
| Community contributions (PRs/Issues) | 4% | 20+ external PRs | GitHub: count merged PRs from non-core contributors in 6 months |
| Enterprise/regulated industry pilots | 5% | 3+ pilot orgs | Count organizations running NexusAI in a production or pilot context |

## 6.5 Dimension 5: Security & Privacy (Weight: 10%)

Critical for regulated industry adoption. Measures how well the platform protects data.

| Dimension | Weight | Target Score | Measurement Method |
| --- | --- | --- | --- |
| PII detection accuracy | 5% | ≥ 95% recall | Test dataset: 1,000 text samples with/without PII. Measure recall & precision |
| Zero PII-flagged data sent to cloud | 5% | 100% enforcement | Audit logs: verify no cloud API call contains PII-flagged content |

## 6.6 Dimension 6: Extensibility & Ecosystem (Weight: 10%)

Measures the long-term platform potential — can others build on top of NexusAI?

| Dimension | Weight | Target Score | Measurement Method |
| --- | --- | --- | --- |
| Plugin/skill API design quality | 4% | External dev can build plugin in < 2 hrs | Measure time for an unfamiliar developer to publish a working plugin |
| Number of community plugins | 3% | 10+ plugins at v2 launch | Count plugins published to NexusAI marketplace / GitHub org |
| Supported LLM providers | 3% | ≥ 8 providers | Count: OpenAI, Anthropic, Google, Mistral, Groq, local models, etc. |

## 6.7 Composite Success Score Summary

| Dimension | Weight | MVP Target | v2 Target | v3 Target |
| --- | --- | --- | --- | --- |
| Technical Execution | 25% | 18/25 | 22/25 | 24/25 |
| Cost Effectiveness | 20% | 14/20 | 17/20 | 19/20 |
| Developer Experience | 20% | 14/20 | 17/20 | 19/20 |
| Market Traction | 15% | 8/15 | 12/15 | 14/15 |
| Security & Privacy | 10% | 8/10 | 9/10 | 10/10 |
| Extensibility & Ecosystem | 10% | 5/10 | 8/10 | 10/10 |
| TOTAL COMPOSITE SCORE | 100% | 67/100 (MVP) | 85/100 (Growth) | 96/100 (Leader) |

Score Interpretation: < 60 = Not ready for launch ¦ 60–74 = Early access / beta ¦ 75–84 = Production ready ¦ 85–94 = Market leader ¦ 95+ = Category defining

# 7. Go-To-Market Strategy

## 7.1 Initial Positioning

Position NexusAI first as a developer tool for regulated industries — specifically fintech, healthcare, and legal — where the value of keeping sensitive data local is a compliance requirement, not just a preference. This creates a strong, defensible initial wedge before expanding to the broader developer market.

## 7.2 Launch Sequence

- Month 1: Open source release on GitHub with strong README, demo video, and one-command Docker install

- Month 2: Post on Hacker News (Show HN), ProductHunt, and DevOps/Fintech communities

- Month 3: Fintech developer conference presence + case study with a regulated industry pilot

- Month 4-6: VS Code marketplace publish, IDE plugin distribution, YouTube tutorial series

- Month 6+: Partner with Ollama, LiteLLM communities for co-promotion; enterprise pilot program

## 7.3 Monetization Path (when ready)

- Core platform: Always free and open source (MIT license)

- NexusAI Cloud: Managed hosted version with pre-configured cloud LLM connections ($20–50/mo)

- NexusAI Enterprise: SSO, audit logs, compliance reports, priority support, SLA ($500+/mo)

- Plugin marketplace: Revenue share on premium community plugins (70/30 split)

# 8. Risk Assessment & Mitigations

| Risk | Severity | Description | Mitigation |
| --- | --- | --- | --- |
| Local LLM hardware requirements | High | Quantized models need 8–16GB RAM minimum; users with low-spec machines cannot run local inference | Offer cloud-only mode for low-spec users; document minimum hardware clearly; support Apple Silicon MPS and CUDA |
| Cloud API rate limits during fallback | Medium | If local model fails and cloud API is rate-limited, requests fail entirely | Multi-provider failover chain: Anthropic → OpenAI → Groq; queue requests with retry logic |
| Automation platform fragmentation | High | macOS/Win/Linux automation APIs differ significantly; maintenance burden is high | Prioritize Linux and macOS first; use Playwright for browser (cross-platform); Win32 API abstraction layer |
| iOS automation restrictions | High | Apple restricts third-party automation significantly on iOS | Position iOS as 'limited' in v3; use Shortcuts API bridge; document limitations clearly |
| Quality gap between local and cloud LLMs | Medium | Users may get poor outputs from local models on tasks that need cloud quality | PQ (quality) routing: if task is flagged as requiring high quality, override cost routing; user-configurable quality thresholds |
| Competitor copies the routing feature | Medium | LiteLLM or AnythingLLM could add intelligent routing | Win on the integrated experience — routing alone is not the moat; automation + coding agent + routing together create the moat |

# 9. Conclusion & Next Steps

NexusAI addresses a genuine gap in the current AI tooling market. The combination of intelligent LLM routing, an integrated coding agent, and cross-platform automation in a single free platform creates a moat that no existing tool currently has. The Success Index provides a clear, measurable framework for tracking progress from MVP through market leadership.

Recommended Immediate Next Steps - Set up GitHub repository with MIT license, strong README, and Docker Compose quickstart - Build the router core using LiteLLM + Ollama — this is the foundation everything else sits on - Define the router config schema (YAML/JSON) to support token thresholds, PII rules, and budget caps - Recruit 5 beta testers from fintech or DevOps community to validate MVP routing accuracy - Track Success Index scores monthly from day one — baseline everything before v1 launch

— NexusAI Platform Blueprint v1.0 — February 2026 —